## Schedule1.0
PROJECT SCHEDULE & MILESTONE CHART
| Project Name : | I8243 MCS-48 Input Out Expander (UF+ Digital)
| Company : | Teradyne (Asia) Pte Ltd |  |  | Project In-charge :
| Customer Contact : | n/a |  |  | Project Description : | To verify I8243 is in good conditions as per SOW's key deliverables.
Start Date :
|  |  | WW33 | WW33 | WW33 | WW33 | WW33 | WW25 | WW27 | WW27 | WW27 | WW27 | WW28 | WW28 | WW28 | WW28 | WW28 | WW29 | WW29 | WW29 | WW29 | WW30 | WW30
S/N : | TASKS |  | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-09-02 | 2024-09-03 | NOTES
1 | Schedule (PMP) | [22 empty] | Planned
Actual
2 | Statement of Work (SOW)
3 | Personal Skills Assessment ( Before start SEP )
4 | GIT setup
5 | Review schedule with Mentor
6 | Test lists
7 | Test Program Coding (Offline) - schedule meeting with Mentor
8 | Test Program Coding (Offline) - Continuity
9 | Test Program Coding (Offline) - ICC & Leakage
Test Program Coding (Offline) - Functional
10 | Test Program Coding (Offline) - Frequency
11 | Test Program Coding (Offline) - Rise & Fall Time
Optional:Test Program Coding (Offline) - SCAN
12 | Test Program Online Debug - Continuity
13 | Test Program Online Debug - ICC & Leakage
14 | Test Program Online Debug - Functional
Test Program Online Debug - Frequency
15 | Test Program Online Debug - Rise & Fall Time
Optional:Test Program Online Debug - SCAN
Correlation & Acceptance - Test flow check
Correlation & Acceptance - Open Socket check
Correlation & Acceptance - Test Time Profile
16 | Correlation & Acceptance - Spike Check
17 | Correlation & Acceptance - Repeatibility (50 loops)
18 | Correlation & Acceptance - Functional Check ( Waveform Diagram and Shmoo )
18 | Wrap Up - Schedule meeting with Mentor
19 | Wrap Up - SEP wrap up (ppt)
20 | Wrap Up - Personal Skills Assessment (After)
21 | Wrap Up - Upload final test program and correlation data to GIT ( check steps for best practise )
22 | Wrap Up - Schedule meeting with Mentor
23
24
25
26
27
#REF!
#REF!
#REF!
Rev.
|  | Timeline : |  | Planned | [19 empty] | Dated
Actual
Holiday
|  | Milestones : |  | Milestone 1: Midreview
Milestone 2: Bin 1 and correlated test program
Milestone 3: Project presentation
Formulas:
WW33 = [WW33]+1
WW33 = [Project In-charge :]+1
Project In-charge : = [WW33]+1
WW25 = [WW33]+1
WW27 = [WW25]+1
WW28 = [WW27]+1
WW29 = [WW28]+1
WW30 = [WW29]+3